## Input
(1) CONCEPT + DECISION: Project Status
Project information
Project Number |  |  |  | 1111E.001236 | [7 empty] | D&D location | [11 empty] | Responsible Purchasing | [10 empty] | Status Today
Project Name |  |  |  | APS VW MEB | [7 empty] | Production location | [5 empty] | HSE | [5 empty] | Project Management | [5 empty] | Gu Jeff |  |  |  |  | Status Future
Customer | [23 empty] | Development Engineer
SQA-TtM
Volumes
Year |  |  |  | 2018 | [32 empty] | SUM
Project Timing | [6 empty] | Project Risks
Milestone |  |  | Date |  |  |  | Main Project Risks | [5 empty] | Description
Run@Rate | [6 empty] | Timing
Start PV | [6 empty] | Quality
SOP Hella |  |  | 01.10.2020 |  |  |  | Costs
SOP Customer
Timing Single Part(s) | [24 empty] | Further comment
|  |  | Part #1 |  |  |  |  | Part #2 | [5 empty] | Part #3 |  |  |  |  | Part #4
Part No. |  |  | 178.576-15 |  |  |  |  | 191.674-01 | [5 empty] | 229.847-00 |  |  |  |  | 234.536-00
Description |  |  | FEDER MONT-GR |  |  |  |  | STECKER GEHAEUSE MONT-GR | [5 empty] | BEDIENELEMENT |  |  |  |  | GEHAEUSE MONT-GR
B-Samples (if applicable)
Sourcing
Availibility
Series Production
Sourcing | [7 empty] | 2019-04-12 00:00:00
FOT
C-Samples available
PPAP released | [7 empty] | 2019-08-02 00:00:00
Additional information
considered tooling leadtime until PPAP
est. tool loops
(2) CONCEPT + DECISION: Total BOM overview
| Part Number |  | Description |  |  |  | PVO (over lifetime) | [15 empty] | Nominated supplier | [5 empty] | Quick Savings
[7 empty] | Target |  |  |  | Current value |  |  |  | Currency |  | Status |  |  | Saving | [8 empty] | yes / no |  |  | based on … | [5 empty] | Value |  |  | Currency
1 | 234.536-00 |  | GEHAEUSE MONT-GR | [7 empty] | 14018792
2 | [44 empty] | - | all mechanical parts of BOM to be mentioned
3 | [44 empty] | - | electr. parts as cost drivers to be mentioned directly
4 | [44 empty] | - | further electr. parts to be mentioned as bundle
5
6
7
8
9
10
11
12
13
14
15
SUM | [22 empty] | <-- enter the cumulated sum of positive and negative savings from overall BOM costs
(3)_CONCEPT: Status Single Component
# | Part No |  | Part Description | [5 empty] | Status |  | Material Group |  |  |  |  | Target PVO |  |  |  | Currency |  | Sourcing Level |  |  |  | Planned Nomination Date | [5 empty] | TOP 1 Tactic |  |  | TOP 2 Tactic |  |  | TOP 3 Tactic |  |  |  | Special requirements: Part (Material & Technology & Testing) | [5 empty] | Special requirements: Packaging
1 | [10 empty] | MET_EXTRU | [8 empty] | CNY
Reference Tactics:
2nd Source
2 | [10 empty] | TECH_PLAS |  |  |  |  | 14229923.2384 |  |  |  | CNY | [5 empty] | 2019-04-12 00:00:00 | [27 empty] | Multiple Source
Sourcing Area: Best Cost
Sourcing Area: local to local
Sourcing Area: based on customer requirements
3 | [10 empty] | TECH_PLAS |  |  |  |  | 19410800 |  |  |  | CNY | [33 empty] | Maturity: Low
Involvement of Development Supplier
Bundling: with other projects
Bundling: with other parts in the project
4 | [10 empty] | TECH_PLAS |  |  |  |  | 14018792 |  |  |  | CNY | [33 empty] | Bundling: with other customer demands
Bundling: with other production locations
Last Call
Auction
[5 empty] | Potential Supplier 1 | [6 empty] | Potential Supplier 2 | [5 empty] | Potential Supplier 3 | [5 empty] | Potential Supplier 4 | [5 empty] | Potential Supplier 5 |  |  |  |  | Potential Supplier 6 | [10 empty] | Potential Supplier 1 |  |  |  | Potential Supplier 2 |  |  | Potential Supplier 3 |  |  | Potential Supplier 4 |  |  |  | Potential Supplier 5 |  |  | Potential Supplier 6
# | Supplier Name | [38 empty] | # | Supplier Name
1 | current Supplier Rating | [38 empty] | 2 | current Supplier Rating
| Contract Status | [39 empty] | Contract Status
| PPM rate (GE Global) | [39 empty] | PPM rate (GE Global)
| Escalation Level | [39 empty] | Escalation Level
| Released Production Plant (city, country) | [39 empty] | Released Production Plant (city, country)
| Benchmark | [39 empty] | Benchmark
[5 empty] | Potential Supplier 1 | [6 empty] | Potential Supplier 2 | [5 empty] | Potential Supplier 3 | [5 empty] | Potential Supplier 4 | [5 empty] | Potential Supplier 5 |  |  |  |  | Potential Supplier 6 | [10 empty] | Potential Supplier 1 |  |  |  | Potential Supplier 2 |  |  | Potential Supplier 3 |  |  | Potential Supplier 4 |  |  |  | Potential Supplier 5 |  |  | Potential Supplier 6
# | Supplier Name | [38 empty] | # | Supplier Name
3 | current Supplier Rating | [38 empty] | 4 | current Supplier Rating
| Contract Status | [39 empty] | Contract Status
| PPM rate (GE Global) | [39 empty] | PPM rate (GE Global)
| Escalation Level | [39 empty] | Escalation Level
| Released Production Plant (city, country) | [39 empty] | Released Production Plant (city, country)
| Benchmark | [39 empty] | Benchmark
(4)_DECISION: General Supplier Status
[11 empty] | 1 | [32 empty] | 2 | [22 empty] | 3 | [16 empty] | 4
Part Number | [34 empty] | Part Number | [23 empty] | Part Number | [17 empty] | Part Number
Supplier name: | [34 empty] | Supplier name: | [23 empty] | Supplier name: | [17 empty] | Supplier name:
Contracts |  |  | Framework Supply Agreement | [31 empty] | Contracts |  |  | Framework Supply Agreement | [20 empty] | Contracts |  |  | Framework Supply Agreement | [14 empty] | Contracts |  |  | Framework Supply Agreement
|  |  | Delivery Reg. for Order Proc. | [34 empty] | Delivery Reg. for Order Proc. | [23 empty] | Delivery Reg. for Order Proc. | [17 empty] | Delivery Reg. for Order Proc.
|  |  | Tool Contract (A/B) | [34 empty] | Tool Contract (A/B) | [23 empty] | Tool Contract (A/B) | [17 empty] | Tool Contract (A/B)
|  |  | Quality Management (HP-C-509) | [34 empty] | Quality Management (HP-C-509) | [23 empty] | Quality Management (HP-C-509) | [17 empty] | Quality Management (HP-C-509)
|  |  | Logistics Guideline (HP-C-516) | [34 empty] | Logistics Guideline (HP-C-516) | [23 empty] | Logistics Guideline (HP-C-516) | [17 empty] | Logistics Guideline (HP-C-516)
Supplier released (for designated Hella Plant) | [34 empty] | Supplier released (for designated Hella Plant) | [23 empty] | Supplier released (for designated Hella Plant) | [17 empty] | Supplier released (for designated Hella Plant)
Approved production location of supplier | [34 empty] | Approved production location of supplier | [23 empty] | Approved production location of supplier | [17 empty] | Approved production location of supplier
Requested material/technology approved for planned production location | [34 empty] | Requested material/technology approved for planned production location | [23 empty] | Requested material/technology approved for planned production location | [17 empty] | Requested material/technology approved for planned production location
(Last) audit result / Potential Analysis | [34 empty] | (Last) audit result / Potential Analysis | [23 empty] | (Last) audit result / Potential Analysis | [17 empty] | (Last) audit result / Potential Analysis
Escalation Level | [34 empty] | Escalation Level | [23 empty] | Escalation Level | [17 empty] | Escalation Level
PPM FY GE | [34 empty] | PPM FY GE | [23 empty] | PPM FY GE | [17 empty] | PPM FY GE
Agreed PPM target | [34 empty] | Agreed PPM target | [23 empty] | Agreed PPM target | [17 empty] | Agreed PPM target
NQE last 12 months | [34 empty] | NQE last 12 months | [23 empty] | NQE last 12 months | [17 empty] | NQE last 12 months
NQE reimbursed last 12 months | [34 empty] | NQE reimbursed last 12 months | [23 empty] | NQE reimbursed last 12 months | [17 empty] | NQE reimbursed last 12 months
Experience with product group | [34 empty] | Experience with product group | [23 empty] | Experience with product group | [17 empty] | Experience with product group
Supplier Risk Assessment (acc. HF-00432) | [34 empty] | Supplier Risk Assessment (acc. HF-00432) | [23 empty] | Supplier Risk Assessment (acc. HF-00432) | [17 empty] | Supplier Risk Assessment (acc. HF-00432)
Logistic Data Sheet (HF-1178_C) | [34 empty] | Logistic Data Sheet (HF-1178_C) | [23 empty] | Logistic Data Sheet (HF-1178_C) | [17 empty] | Logistic Data Sheet (HF-1178_C)
Packaging Data Sheet | [34 empty] | Packaging Data Sheet | [23 empty] | Packaging Data Sheet | [17 empty] | Packaging Data Sheet
Sub-Supplier Management | [34 empty] | Sub-Supplier Management | [23 empty] | Sub-Supplier Management | [17 empty] | Sub-Supplier Management
Product Safety Representative implemented | [34 empty] | Product Safety Representative implemented | [23 empty] | Product Safety Representative implemented | [17 empty] | Product Safety Representative implemented
(5) DECISION: Sourcing Approval
[7 empty] | #1 | [29 empty] | #2 | [19 empty] | #3 | [15 empty] | #4
[7 empty] | HELLA VALUES |  |  |  |  | Team proposal | [5 empty] | Alternative 1 | [5 empty] | Alternative 2 | [12 empty] | HELLA VALUES |  |  |  | Team proposal |  |  |  |  | Alternative 1 |  |  |  | Alternative 2 | [6 empty] | HELLA VALUES |  |  |  | Team proposal |  |  | Alternative 1 |  |  |  | Alternative 2 |  |  |  |  | HELLA VALUES |  | Team proposal |  |  |  | Alternative 1 |  |  | Alternative 2
Part Number: | [30 empty] | Part Number: | [22 empty] | Part Number: | [15 empty] | Part Number:
Nomination Roadmap | [30 empty] | Nomination Roadmap | [22 empty] | Nomination Roadmap | [15 empty] | Nomination Roadmap
Planned lifetime quantity | [30 empty] | Planned lifetime quantity | [22 empty] | Planned lifetime quantity | [15 empty] | Planned lifetime quantity
Cost Share towards BOM | [30 empty] | Cost Share towards BOM | [22 empty] | Cost Share towards BOM | [15 empty] | Cost Share towards BOM
Sourcing Level | [30 empty] | Sourcing Level | [22 empty] | Sourcing Level | [15 empty] | Sourcing Level
Status drawing | [30 empty] | Status drawing | [22 empty] | Status drawing | [15 empty] | Status drawing
Customer nomination available | [30 empty] | Customer nomination available | [22 empty] | Customer nomination available | [15 empty] | Customer nomination available
Budget available | [30 empty] | Budget available | [22 empty] | Budget available | [15 empty] | Budget available
Concept presented | [30 empty] | Concept presented | [22 empty] | Concept presented | [15 empty] | Concept presented
# of suppliers (acc. Supplier Selection Sheet) | [30 empty] | # of suppliers (acc. Supplier Selection Sheet) | [22 empty] | # of suppliers (acc. Supplier Selection Sheet) | [15 empty] | # of suppliers (acc. Supplier Selection Sheet)
# of final received offers | [30 empty] | # of final received offers | [22 empty] | # of final received offers | [15 empty] | # of final received offers
Sourcing Date (final approval) | [30 empty] | Sourcing Date (final approval) | [22 empty] | Sourcing Date (final approval) | [15 empty] | Sourcing Date (final approval)
Supplier name | [30 empty] | Supplier name | [22 empty] | Supplier name | [15 empty] | Supplier name
Currency of quote | [30 empty] | Currency of quote | [22 empty] | Currency of quote | [15 empty] | Currency of quote
Target currency | [30 empty] | Target currency | [22 empty] | Target currency | [15 empty] | Target currency
Exchange rate to target currency | [30 empty] | Exchange rate to target currency | [22 empty] | Exchange rate to target currency | [15 empty] | Exchange rate to target currency
Final part price per 100pcs | [30 empty] | Final part price per 100pcs | [22 empty] | Final part price per 100pcs | [15 empty] | Final part price per 100pcs
Target piece price year 1 / 100pcs | [30 empty] | Target piece price year 1 / 100pcs | [22 empty] | Target piece price year 1 / 100pcs | [15 empty] | Target piece price year 1 / 100pcs
Year 1 | [30 empty] | Year 1 | [22 empty] | Year 1 | [15 empty] | Year 1
Year 2 | [30 empty] | Year 2 | [22 empty] | Year 2 | [15 empty] | Year 2
Year 3 | [30 empty] | Year 3 | [22 empty] | Year 3 | [15 empty] | Year 3
Year 4 | [30 empty] | Year 4 | [22 empty] | Year 4 | [15 empty] | Year 4
Year 5 | [30 empty] | Year 5 | [22 empty] | Year 5 | [15 empty] | Year 5
Tooling & Invest | [30 empty] | Tooling & Invest | [22 empty] | Tooling & Invest | [15 empty] | Tooling & Invest
Target first tool set | [30 empty] | Target first tool set | [22 empty] | Target first tool set | [15 empty] | Target first tool set
Pricing first tool set | [30 empty] | Pricing first tool set | [22 empty] | Pricing first tool set | [15 empty] | Pricing first tool set
Number of cavities | [30 empty] | Number of cavities | [22 empty] | Number of cavities | [15 empty] | Number of cavities
Tool ownership | [30 empty] | Tool ownership | [22 empty] | Tool ownership | [15 empty] | Tool ownership
Target additional invest | [30 empty] | Target additional invest | [22 empty] | Target additional invest | [15 empty] | Target additional invest
Total pricing additional invest | [30 empty] | Total pricing additional invest | [22 empty] | Total pricing additional invest | [15 empty] | Total pricing additional invest
Pricing follow up tools | [30 empty] | Pricing follow up tools | [22 empty] | Pricing follow up tools | [15 empty] | Pricing follow up tools
estimated number follow up tools | [30 empty] | estimated number follow up tools | [22 empty] | estimated number follow up tools | [15 empty] | estimated number follow up tools
PVO | [30 empty] | PVO | [22 empty] | PVO | [15 empty] | PVO
Target PVO (parts+tools+invest) | [30 empty] | Target PVO (parts+tools+invest) | [22 empty] | Target PVO (parts+tools+invest) | [15 empty] | Target PVO (parts+tools+invest)
Total PVO (based on quote) | [30 empty] | Total PVO (based on quote) | [22 empty] | Total PVO (based on quote) | [15 empty] | Total PVO (based on quote)
PVO target deviation | [30 empty] | PVO target deviation | [22 empty] | PVO target deviation | [15 empty] | PVO target deviation
Additional | [30 empty] | Additional | [22 empty] | Additional | [15 empty] | Additional
Cost Break Down | [30 empty] | Cost Break Down | [22 empty] | Cost Break Down | [15 empty] | Cost Break Down
Quick Savings | [30 empty] | Quick Savings | [22 empty] | Quick Savings | [15 empty] | Quick Savings
Negotitated LTAs | [30 empty] | Negotitated LTAs | [22 empty] | Negotitated LTAs | [15 empty] | Negotitated LTAs
DPO | [30 empty] | DPO | [22 empty] | DPO | [15 empty] | DPO
APQP Level | [30 empty] | APQP Level | [22 empty] | APQP Level | [15 empty] | APQP Level
Feasibility Study | [30 empty] | Feasibility Study | [22 empty] | Feasibility Study | [15 empty] | Feasibility Study
Main Risks | [30 empty] | Main Risks | [22 empty] | Main Risks | [15 empty] | Main Risks
Remarks | [30 empty] | Remarks | [22 empty] | Remarks | [15 empty] | Remarks
Final Team Decision | [30 empty] | Final Team Decision | [22 empty] | Final Team Decision | [15 empty] | Final Team Decision
Supplier Name 1st source | [17 empty] | Quota / Share | [5 empty] | % | [6 empty] | Supplier Name 1st source | [14 empty] | Quota / Share |  |  |  | % |  |  |  | Supplier Name 1st source | [9 empty] | Quota / Share |  |  |  | % |  | Supplier Name 1st source | [8 empty] | Quota / Share |  |  | %
Supplier Name 2nd source | [17 empty] | Quota / Share | [5 empty] | % | [6 empty] | Supplier Name 2nd source | [14 empty] | Quota / Share |  |  |  | % |  |  |  | Supplier Name 2nd source | [9 empty] | Quota / Share |  |  |  | % |  | Supplier Name 2nd source | [8 empty] | Quota / Share |  |  | %
(6) DECISION: Capacity Management
Part 1 |  |  | customer demand |  |  | customer flex. in % |  |  |  | customer flex. |  |  |  | customer demand + flex. |  |  | Supplier Name: | [14 empty] | DELTA |  | Hella |  |  | Part 2 |  |  |  | customer demand |  | customer flex. in % |  |  |  | customer flex. |  | customer demand + flex. |  | Supplier Name: | [6 empty] | DELTA |  |  | Hella |  | Part 3 |  |  | customer demand |  | customer flex. in % | customer flex. | customer demand + flex. | Supplier Name: | [6 empty] | DELTA |  |  | Hella |  | Part 4 |  |  | customer demand | customer flex. in % | customer flex. | customer demand + flex. | Supplier Name: |  |  |  | DELTA | Hella
[17 empty] | supplier demand |  |  |  | supplier flex. in % |  |  | supplier flex. |  |  | supplier demand + flex. | [23 empty] | supplier demand | supplier flex. in % |  |  | supplier flex. | supplier demand + flex. | [14 empty] | supplier demand | supplier flex. in % |  | supplier flex. |  | supplier demand + flex. | [13 empty] | supplier demand | supplier flex. in % | supplier flex. | supplier demand + flex.
|  | 2018 | [36 empty] | 2018 | [25 empty] | 2018 | [19 empty] | 2018
Ø Flexibility | [36 empty] | Ø Flexibility | [25 empty] | Ø Flexibility | [19 empty] | Ø Flexibility
Flexibility leadtime (weeks) | [36 empty] | Flexibility leadtime (weeks) | [25 empty] | Flexibility leadtime (weeks) | [19 empty] | Flexibility leadtime (weeks)
Flexibility Duration | [36 empty] | Flexibility Duration | [25 empty] | Flexibility Duration | [19 empty] | Flexibility Duration
shifts / week | [36 empty] | shifts / week | [25 empty] | shifts / week | [19 empty] | shifts / week
weeks / year | [36 empty] | weeks / year | [25 empty] | weeks / year | [19 empty] | weeks / year
Comment | [36 empty] | Comment | [25 empty] | Comment | [19 empty] | Comment
(7) DECISION: Counter Measures for target achievement
| Part No |  | Part Description |  |  |  |  | Target PVO |  |  |  | Value over target |  |  |  |  | Currency |  |  |  | Activities | [6 empty] | Value of counter measure |  |  |  |  | Currency |  |  | Final due date |  |  | Degree of fulfillment |  |  |  | Responsible
1
2
3
4
5
6
7
8
9
10
(8) DECISION: Team recommendation
Department | [6 empty] | Name | [8 empty] | Recommended Supplier
Program Purchasing
Project Management
Material Group Specialist / Manager
Product Cost Management
SQA TtM
Mechanical Design (if applicable)
Hardware Design (if applicable)
Plant Logistics
Manufacturing Engineer
Final Decision: Project Team
(9) CONCEPT + DECISION: Open points and activities
Topic | [18 empty] | Responsible | [6 empty] | Due date