## Input
(1) CONCEPT + DECISION: Project Status
Project information
Project Number |  |  |  | demo | [7 empty] | D&D location | [11 empty] | Responsible Purchasing | [12 empty] | Status Today
Project Name |  |  |  | name | [7 empty] | Production location | [11 empty] | Project Management | [12 empty] | Status Future
Customer | [23 empty] | Development Engineer
SQA-TtM
Volumes
Year |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  | 2027 |  | SUM
Project Timing | [6 empty] | Project Risks
Milestone |  |  | Date |  |  |  | Main Project Risks | [5 empty] | Description
Run@Rate | [6 empty] | Timing | [5 empty] | timing issue
Start PV | [6 empty] | Quality | [5 empty] | qty issue xxx.
SOP Hella | [6 empty] | Costs | [5 empty] | cost issue xxx.
SOP Customer
Timing Single Part(s) | [24 empty] | Further comment
|  |  | Part #1 |  |  |  |  | Part #2 | [5 empty] | Part #3 |  |  |  |  | Part #4
Part No. |  |  | demo part |  |  |  |  | demo part | [5 empty] | demo part
Description |  |  | des |  |  |  |  | des | [5 empty] | des
B-Samples (if applicable)
Sourcing
Availibility
Series Production
Sourcing
FOT
C-Samples available
PPAP released
Additional information
considered tooling leadtime until PPAP
est. tool loops
(2) CONCEPT + DECISION: Total BOM overview
| Part Number |  | Description |  |  |  | PVO (over lifetime) | [15 empty] | Nominated supplier | [6 empty] | Quick Savings
[7 empty] | Target |  |  |  | Current value |  |  |  | Currency |  | Status |  |  | Saving | [9 empty] | yes / no |  |  | based on … | [6 empty] | Value |  |  | Currency
1 | [19 empty] | 0
2 | [19 empty] | 0 | [26 empty] | - | all mechanical parts of BOM to be mentioned
3 | [19 empty] | 0 | [26 empty] | - | electr. parts as cost drivers to be mentioned directly
4 | [19 empty] | 0 | [26 empty] | - | further electr. parts to be mentioned as bundle
5 | [19 empty] | 0
6 | [19 empty] | 0
7 | [19 empty] | 0
8 | [19 empty] | 0
9 | [19 empty] | 0
10 | [19 empty] | 0
11 | [19 empty] | 0
12 | [19 empty] | 0
13 | [19 empty] | 0
14 | [19 empty] | 0
15 | [19 empty] | 0
SUM | [22 empty] | <-- enter the cumulated sum of positive and negative savings from overall BOM costs
(3)_CONCEPT: Status Single Component
# | Part No |  | Part Description | [5 empty] | Status |  | Material Group |  |  |  |  | Target PVO |  |  |  | Currency |  | Sourcing Level |  |  |  |  | Planned Nomination Date | [5 empty] | TOP 1 Tactic |  |  |  | TOP 2 Tactic |  |  | TOP 3 Tactic |  |  |  | Special requirements: Part (Material & Technology & Testing) | [5 empty] | Special requirements: Packaging
1 | demo part |  | des
Reference Tactics:
2nd Source
2 | demo part |  | des | [52 empty] | Multiple Source
Sourcing Area: Best Cost
Sourcing Area: local to local
Sourcing Area: based on customer requirements
3 | demo part |  | des | [52 empty] | Maturity: Low
Involvement of Development Supplier
Bundling: with other projects
Bundling: with other parts in the project
4 | [55 empty] | Bundling: with other customer demands
Bundling: with other production locations
Last Call
Auction
| demo part |  |  |  | Potential Supplier 1 | [6 empty] | Potential Supplier 2 | [5 empty] | Potential Supplier 3 | [5 empty] | Potential Supplier 4 | [6 empty] | Potential Supplier 5 | [5 empty] | Potential Supplier 6 | [5 empty] | demo part |  |  |  |  | Potential Supplier 1 |  |  |  | Potential Supplier 2 |  |  | Potential Supplier 3 |  |  | Potential Supplier 4 |  |  |  | Potential Supplier 5 |  |  | Potential Supplier 6
# | Supplier Name | [40 empty] | # | Supplier Name
1 | current Supplier Rating | [40 empty] | 2 | current Supplier Rating
| Contract Status | [41 empty] | Contract Status
| PPM rate (GE Global) | [41 empty] | PPM rate (GE Global)
| Escalation Level | [41 empty] | Escalation Level
| Released Production Plant (city, country) | [41 empty] | Released Production Plant (city, country)
| Benchmark | [41 empty] | Benchmark
| demo part |  |  |  | Potential Supplier 1 | [6 empty] | Potential Supplier 2 | [5 empty] | Potential Supplier 3 | [5 empty] | Potential Supplier 4 | [6 empty] | Potential Supplier 5 | [5 empty] | Potential Supplier 6 | [10 empty] | Potential Supplier 1 |  |  |  | Potential Supplier 2 |  |  | Potential Supplier 3 |  |  | Potential Supplier 4 |  |  |  | Potential Supplier 5 |  |  | Potential Supplier 6
# | Supplier Name | [40 empty] | # | Supplier Name
3 | current Supplier Rating | [40 empty] | 4 | current Supplier Rating
| Contract Status | [41 empty] | Contract Status
| PPM rate (GE Global) | [41 empty] | PPM rate (GE Global)
| Escalation Level | [41 empty] | Escalation Level
| Released Production Plant (city, country) | [41 empty] | Released Production Plant (city, country)
| Benchmark | [41 empty] | Benchmark
(4)_DECISION: General Supplier Status
[11 empty] | 1 | [34 empty] | 2 | [22 empty] | 3 | [16 empty] | 4
Part Number | [10 empty] | demo part | [25 empty] | Part Number | [8 empty] | demo part | [14 empty] | Part Number | [7 empty] | demo part | [9 empty] | Part Number
Supplier name: | [36 empty] | Supplier name: | [23 empty] | Supplier name: | [17 empty] | Supplier name:
Contracts |  |  | Framework Supply Agreement | [33 empty] | Contracts |  |  | Framework Supply Agreement | [20 empty] | Contracts |  |  | Framework Supply Agreement | [14 empty] | Contracts |  |  | Framework Supply Agreement
|  |  | Delivery Reg. for Order Proc. | [36 empty] | Delivery Reg. for Order Proc. | [23 empty] | Delivery Reg. for Order Proc. | [17 empty] | Delivery Reg. for Order Proc.
|  |  | Tool Contract (A/B) | [36 empty] | Tool Contract (A/B) | [23 empty] | Tool Contract (A/B) | [17 empty] | Tool Contract (A/B)
|  |  | Quality Management (HP-C-509) | [36 empty] | Quality Management (HP-C-509) | [23 empty] | Quality Management (HP-C-509) | [17 empty] | Quality Management (HP-C-509)
|  |  | Logistics Guideline (HP-C-516) | [36 empty] | Logistics Guideline (HP-C-516) | [23 empty] | Logistics Guideline (HP-C-516) | [17 empty] | Logistics Guideline (HP-C-516)
Supplier released (for designated Hella Plant) | [36 empty] | Supplier released (for designated Hella Plant) | [23 empty] | Supplier released (for designated Hella Plant) | [17 empty] | Supplier released (for designated Hella Plant)
Approved production location of supplier | [36 empty] | Approved production location of supplier | [23 empty] | Approved production location of supplier | [17 empty] | Approved production location of supplier
Requested material/technology approved for planned production location | [36 empty] | Requested material/technology approved for planned production location | [23 empty] | Requested material/technology approved for planned production location | [17 empty] | Requested material/technology approved for planned production location
(Last) audit result / Potential Analysis | [36 empty] | (Last) audit result / Potential Analysis | [23 empty] | (Last) audit result / Potential Analysis | [17 empty] | (Last) audit result / Potential Analysis
Escalation Level | [36 empty] | Escalation Level | [23 empty] | Escalation Level | [17 empty] | Escalation Level
PPM FY GE | [36 empty] | PPM FY GE | [23 empty] | PPM FY GE | [17 empty] | PPM FY GE
Agreed PPM target | [36 empty] | Agreed PPM target | [23 empty] | Agreed PPM target | [17 empty] | Agreed PPM target
NQE last 12 months | [36 empty] | NQE last 12 months | [23 empty] | NQE last 12 months | [17 empty] | NQE last 12 months
NQE reimbursed last 12 months | [36 empty] | NQE reimbursed last 12 months | [23 empty] | NQE reimbursed last 12 months | [17 empty] | NQE reimbursed last 12 months
Experience with product group | [36 empty] | Experience with product group | [23 empty] | Experience with product group | [17 empty] | Experience with product group
Supplier Risk Assessment (acc. HF-00432) | [36 empty] | Supplier Risk Assessment (acc. HF-00432) | [23 empty] | Supplier Risk Assessment (acc. HF-00432) | [17 empty] | Supplier Risk Assessment (acc. HF-00432)
Logistic Data Sheet (HF-1178_C) | [36 empty] | Logistic Data Sheet (HF-1178_C) | [23 empty] | Logistic Data Sheet (HF-1178_C) | [17 empty] | Logistic Data Sheet (HF-1178_C)
Packaging Data Sheet | [36 empty] | Packaging Data Sheet | [23 empty] | Packaging Data Sheet | [17 empty] | Packaging Data Sheet
Sub-Supplier Management | [36 empty] | Sub-Supplier Management | [23 empty] | Sub-Supplier Management | [17 empty] | Sub-Supplier Management
Product Safety Representative implemented | [36 empty] | Product Safety Representative implemented | [23 empty] | Product Safety Representative implemented | [17 empty] | Product Safety Representative implemented
(5) DECISION: Sourcing Approval
[7 empty] | #1 | [31 empty] | #2 | [19 empty] | #3 | [15 empty] | #4
[7 empty] | HELLA VALUES |  |  |  |  | Team proposal | [5 empty] | Alternative 1 | [5 empty] | Alternative 2 | [14 empty] | HELLA VALUES |  |  |  | Team proposal |  |  |  |  | Alternative 1 |  |  |  | Alternative 2 | [6 empty] | HELLA VALUES |  |  |  | Team proposal |  |  | Alternative 1 |  |  |  | Alternative 2 |  |  |  |  | HELLA VALUES |  | Team proposal |  |  |  | Alternative 1 |  |  | Alternative 2
Part Number: | [6 empty] | demo part | [24 empty] | Part Number: | [6 empty] | demo part | [16 empty] | Part Number: |  |  | demo part | [12 empty] | Part Number:
Nomination Roadmap | [31 empty] | Nomination Roadmap | [23 empty] | Nomination Roadmap | [15 empty] | Nomination Roadmap
Planned lifetime quantity | [31 empty] | Planned lifetime quantity | [23 empty] | Planned lifetime quantity | [15 empty] | Planned lifetime quantity
Cost Share towards BOM | [31 empty] | Cost Share towards BOM | [23 empty] | Cost Share towards BOM | [15 empty] | Cost Share towards BOM
Sourcing Level | [31 empty] | Sourcing Level | [23 empty] | Sourcing Level | [15 empty] | Sourcing Level
Status drawing | [31 empty] | Status drawing | [23 empty] | Status drawing | [15 empty] | Status drawing
Customer nomination available | [31 empty] | Customer nomination available | [23 empty] | Customer nomination available | [15 empty] | Customer nomination available
Budget available | [31 empty] | Budget available | [23 empty] | Budget available | [15 empty] | Budget available
Concept presented | [31 empty] | Concept presented | [23 empty] | Concept presented | [15 empty] | Concept presented
# of suppliers (acc. Supplier Selection Sheet) | [31 empty] | # of suppliers (acc. Supplier Selection Sheet) | [23 empty] | # of suppliers (acc. Supplier Selection Sheet) | [15 empty] | # of suppliers (acc. Supplier Selection Sheet)
# of final received offers | [31 empty] | # of final received offers | [23 empty] | # of final received offers | [15 empty] | # of final received offers
Sourcing Date (final approval) | [31 empty] | Sourcing Date (final approval) | [23 empty] | Sourcing Date (final approval) | [15 empty] | Sourcing Date (final approval)
Supplier name | [11 empty] | ace | [5 empty] | rosti | [5 empty] | ata | [7 empty] | Supplier name | [23 empty] | Supplier name | [15 empty] | Supplier name
Currency of quote | [31 empty] | Currency of quote | [23 empty] | Currency of quote | [15 empty] | Currency of quote
Target currency | [31 empty] | Target currency | [23 empty] | Target currency | [15 empty] | Target currency
Exchange rate to target currency | [31 empty] | Exchange rate to target currency | [23 empty] | Exchange rate to target currency | [15 empty] | Exchange rate to target currency
Final part price per 100pcs | [31 empty] | Final part price per 100pcs | [23 empty] | Final part price per 100pcs | [15 empty] | Final part price per 100pcs
Target piece price year 1 / 100pcs | [31 empty] | Target piece price year 1 / 100pcs | [23 empty] | Target piece price year 1 / 100pcs | [15 empty] | Target piece price year 1 / 100pcs
Year 1 | [31 empty] | Year 1 | [23 empty] | Year 1 | [15 empty] | Year 1
Year 2 | [31 empty] | Year 2 | [23 empty] | Year 2 | [15 empty] | Year 2
Year 3 | [31 empty] | Year 3 | [23 empty] | Year 3 | [15 empty] | Year 3
Year 4 | [31 empty] | Year 4 | [23 empty] | Year 4 | [15 empty] | Year 4
Year 5 | [31 empty] | Year 5 | [23 empty] | Year 5 | [15 empty] | Year 5
Tooling & Invest | [31 empty] | Tooling & Invest | [23 empty] | Tooling & Invest | [15 empty] | Tooling & Invest
Target first tool set | [31 empty] | Target first tool set | [23 empty] | Target first tool set | [15 empty] | Target first tool set
Pricing first tool set | [31 empty] | Pricing first tool set | [23 empty] | Pricing first tool set | [15 empty] | Pricing first tool set
Number of cavities | [31 empty] | Number of cavities | [23 empty] | Number of cavities | [15 empty] | Number of cavities
Tool ownership | [31 empty] | Tool ownership | [23 empty] | Tool ownership | [15 empty] | Tool ownership
Target additional invest | [31 empty] | Target additional invest | [23 empty] | Target additional invest | [15 empty] | Target additional invest
Total pricing additional invest | [31 empty] | Total pricing additional invest | [23 empty] | Total pricing additional invest | [15 empty] | Total pricing additional invest
Pricing follow up tools | [31 empty] | Pricing follow up tools | [23 empty] | Pricing follow up tools | [15 empty] | Pricing follow up tools
estimated number follow up tools | [31 empty] | estimated number follow up tools | [23 empty] | estimated number follow up tools | [15 empty] | estimated number follow up tools
PVO | [31 empty] | PVO | [23 empty] | PVO | [15 empty] | PVO
Target PVO (parts+tools+invest) | [6 empty] | 10000 | [24 empty] | Target PVO (parts+tools+invest) | [23 empty] | Target PVO (parts+tools+invest) | [15 empty] | Target PVO (parts+tools+invest)
Total PVO (based on quote) | [11 empty] | 12000 | [5 empty] | 8000 | [5 empty] | 10000 | [7 empty] | Total PVO (based on quote) | [23 empty] | Total PVO (based on quote) | [15 empty] | Total PVO (based on quote)
PVO target deviation | [11 empty] | -2000 | [5 empty] | 2000 | [5 empty] | 0 | [7 empty] | PVO target deviation | [23 empty] | PVO target deviation | [15 empty] | PVO target deviation
Additional | [31 empty] | Additional | [23 empty] | Additional | [15 empty] | Additional
Cost Break Down | [31 empty] | Cost Break Down | [23 empty] | Cost Break Down | [15 empty] | Cost Break Down
Quick Savings | [31 empty] | Quick Savings | [23 empty] | Quick Savings | [15 empty] | Quick Savings
Negotitated LTAs | [31 empty] | Negotitated LTAs | [23 empty] | Negotitated LTAs | [15 empty] | Negotitated LTAs
DPO | [31 empty] | DPO | [23 empty] | DPO | [15 empty] | DPO
APQP Level | [31 empty] | APQP Level | [23 empty] | APQP Level | [15 empty] | APQP Level
Feasibility Study | [31 empty] | Feasibility Study | [23 empty] | Feasibility Study | [15 empty] | Feasibility Study
Main Risks | [31 empty] | Main Risks | [23 empty] | Main Risks | [15 empty] | Main Risks
Remarks | [31 empty] | Remarks | [23 empty] | Remarks | [15 empty] | Remarks
Final Team Decision | [31 empty] | Final Team Decision | [23 empty] | Final Team Decision | [15 empty] | Final Team Decision
Supplier Name 1st source | [17 empty] | Quota / Share | [5 empty] | % | [7 empty] | Supplier Name 1st source | [15 empty] | Quota / Share |  |  |  | % |  |  |  | Supplier Name 1st source | [9 empty] | Quota / Share |  |  |  | % |  | Supplier Name 1st source | [8 empty] | Quota / Share |  |  | %
Supplier Name 2nd source | [17 empty] | Quota / Share | [5 empty] | % | [7 empty] | Supplier Name 2nd source | [15 empty] | Quota / Share |  |  |  | % |  |  |  | Supplier Name 2nd source | [9 empty] | Quota / Share |  |  |  | % |  | Supplier Name 2nd source | [8 empty] | Quota / Share |  |  | %
(6) DECISION: Capacity Management
Part 1 |  |  | customer demand |  |  | customer flex. in % |  |  |  | customer flex. |  |  |  | customer demand + flex. |  |  | Supplier Name: | [15 empty] | DELTA |  |  | Hella |  |  | Part 2 |  |  |  | customer demand |  | customer flex. in % |  |  |  | customer flex. |  | customer demand + flex. |  | Supplier Name: | [6 empty] | DELTA |  |  | Hella |  | Part 3 |  |  | customer demand |  | customer flex. in % | customer flex. | customer demand + flex. | Supplier Name: | [6 empty] | DELTA |  |  | Hella |  | Part 4 |  |  | customer demand | customer flex. in % | customer flex. | customer demand + flex. | Supplier Name: |  |  |  | DELTA | Hella
demo part | [16 empty] | supplier demand |  |  |  | supplier flex. in % |  |  | supplier flex. |  |  |  | supplier demand + flex. | [10 empty] | demo part | [13 empty] | supplier demand | supplier flex. in % |  |  | supplier flex. | supplier demand + flex. | [6 empty] | demo part | [7 empty] | supplier demand | supplier flex. in % |  | supplier flex. |  | supplier demand + flex. | [13 empty] | supplier demand | supplier flex. in % | supplier flex. | supplier demand + flex.
|  | 2018 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2018 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2018 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2018 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2019 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2019 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2019 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2019 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2020 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2020 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2020 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2020 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2021 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2021 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2021 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2021 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2022 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2022 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2022 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2022 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2023 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2023 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2023 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2023 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2024 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2024 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2024 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2024 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2025 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2025 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2025 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2025 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2026 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2026 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2026 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2026 |  |  | 0 | 0 |  |  | 0 | 0 | 0
|  | 2027 | [7 empty] | 0 |  |  |  | 0 | [9 empty] | 0 |  |  |  | 0 |  |  |  |  | 0 | [7 empty] | 2027 | [7 empty] | 0 |  | 0 | [5 empty] | 0 | 0 |  | 0 | [6 empty] | 2027 |  |  |  | 0 | 0 |  |  |  | 0 |  | 0 |  | 0 | [6 empty] | 2027 |  |  | 0 | 0 |  |  | 0 | 0 | 0
Ø Flexibility | [5 empty] | #DIV/0! | [14 empty] | #DIV/0! | [17 empty] | Ø Flexibility | [5 empty] | #DIV/0! | [8 empty] | #DIV/0! | [10 empty] | Ø Flexibility |  |  |  |  | #DIV/0! |  |  |  | #DIV/0! | [10 empty] | Ø Flexibility |  |  |  | #DIV/0! |  |  |  | #DIV/0!
Flexibility leadtime (weeks) | [38 empty] | Flexibility leadtime (weeks) | [25 empty] | Flexibility leadtime (weeks) | [19 empty] | Flexibility leadtime (weeks)
Flexibility Duration | [38 empty] | Flexibility Duration | [25 empty] | Flexibility Duration | [19 empty] | Flexibility Duration
shifts / week | [38 empty] | shifts / week | [25 empty] | shifts / week | [19 empty] | shifts / week
weeks / year | [38 empty] | weeks / year | [25 empty] | weeks / year | [19 empty] | weeks / year
Comment | [38 empty] | Comment | [25 empty] | Comment | [19 empty] | Comment
(7) DECISION: Counter Measures for target achievement
| Part No |  | Part Description |  |  |  |  | Target PVO |  |  |  | Value over target |  |  |  |  | Currency |  |  |  | Activities | [7 empty] | Value of counter measure | [5 empty] | Currency |  |  | Final due date |  |  | Degree of fulfillment |  |  |  | Responsible
1
2
3
4
5
6
7
8
9
10
(8) DECISION: Team recommendation
Department | [6 empty] | Name | [8 empty] | Recommended Supplier
Program Purchasing
Project Management
Material Group Specialist / Manager
Product Cost Management
SQA TtM
Mechanical Design (if applicable)
Hardware Design (if applicable)
Plant Logistics
Manufacturing Engineer
Final Decision: Project Team
(9) CONCEPT + DECISION: Open points and activities
Topic | [18 empty] | Responsible | [7 empty] | Due date

## (1) Project Status
Project Information | [7 empty] | Status Today | Main Project Risks |  | Description
Project | demo |  |  | name |  |  |  |  | Timing |  | timing issue
Customer | [8 empty] | Quality |  | qty issue xxx.
D&D location |  |  | Production location |  |  |  |  | Status Future | Costs |  | cost issue xxx.
Responsible Purchasing |  |  | Program Mgmt
Development Engineer |  |  | SQA-TtM
Timeline: Project | [8 empty] | Project Volumes
Milestone |  | Date |  |  | Milestone |  | Date |  | Year
Run@Rate Hella |  |  |  |  | SOP Hella |  |  |  |  | Volumes |  | Volumes | Volumes
Start PV |  |  |  |  | SOP Customer |  |  |  | 2018
2019
Timeline Parts |  | demo part | demo part |  |  | demo part |  |  | 2020
Description |  | des | des |  |  | des |  |  | 2021
B-Samples (if applicable) | [8 empty] | 2022
Sourcing | [8 empty] | 2023
Availability | [8 empty] | 2024
Series Production | [8 empty] | 2025
Sourcing | [8 empty] | 2026
FOT | [8 empty] | 2027
C-Samples | [8 empty] | SUM
PPAP released
cons. tooling leadtime until PPAP
est. tool loops
Further project information

## (2) Total BOM overview
No | Part Number | Description | PVO (over lifetime) |  |  |  |  | Nominated supplier | Quick Savings
|  |  | Target | Current value | Currency | Status | Saving |  | yes / no | based on … | Value | Currency
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
SUM

## (3) Status Single Component
1 | [11 empty] | 2
Part No. | Status | Description |  |  |  | Material Group | Please insert picture / drawing directly in Power Point |  |  |  |  | Part No. | Status | Description |  |  |  | Material Group | Please insert picture / drawing directly in Power Point
demo part |  | des | [9 empty] | demo part |  | des
Target PVO (lifetime / incl. tooling) |  | Sourcing Level |  | Planned Nomination | [7 empty] | Target PVO (lifetime / incl. tooling) |  | Sourcing Level |  | Planned Nomination
Special requirements: Part (Material & Technology & Testing) | [6 empty] | Special requirements: Packaging |  |  |  |  | Special requirements: Part (Material & Technology & Testing) | [6 empty] | Special requirements: Packaging
Top 1 Tactic |  |  |  |  | Top 2 Tactic |  |  |  | Top 3 Tactic |  |  | Top 1 Tactic |  |  |  |  | Top 2 Tactic |  |  |  | Top 3 Tactic
Top Suppliers (acc. respective supplier matrix) |  |  | Supplier Rating |  | Contract Status |  | PPM Rate (GE global) | Escalation Level |  | Released Production Plant | Benchmark | Top Suppliers (acc. respective supplier matrix) |  |  | Supplier Rating |  | Contract Status |  | PPM Rate (GE global) | Escalation Level |  | Released Production Plant | Benchmark
1. | [11 empty] | 1.
2. | [11 empty] | 2.
3. | [11 empty] | 3.
4. | [11 empty] | 4.
5. | [11 empty] | 5.
6. | [11 empty] | 6.
3 | [11 empty] | 4
Part No. | Status | Description |  |  |  | Material Group | Please insert picture / drawing directly in Power Point |  |  |  |  | Part No. | Status | Description |  |  |  | Material Group | Please insert picture / drawing directly in Power Point
demo part |  | des
Target PVO (lifetime / incl. tooling) |  | Sourcing Level |  | Planned Nomination | [7 empty] | Target PVO (lifetime / incl. tooling) |  | Sourcing Level |  | Planned Nomination
Special requirements: Part (Material & Technology & Testing) | [6 empty] | Special requirements: Packaging |  |  |  |  | Special requirements: Part (Material & Technology & Testing) | [6 empty] | Special requirements: Packaging
Top 1 Tactic |  |  |  |  | Top 2 Tactic |  |  |  | Top 3 Tactic |  |  | Top 1 Tactic |  |  |  |  | Top 2 Tactic |  |  |  | Top 3 Tactic
Top Suppliers (acc. respective supplier matrix) |  |  | Supplier Rating |  | Contract Status |  | PPM Rate (GE global) | Escalation Level |  | Released Production Plant | Benchmark | Top Suppliers (acc. respective supplier matrix) |  |  | Supplier Rating |  | Contract Status |  | PPM Rate (GE global) | Escalation Level |  | Released Production Plant | Benchmark
1. | [11 empty] | 1.
2. | [11 empty] | 2.
3. | [11 empty] | 3.
4. | [11 empty] | 4.
5. | [11 empty] | 5.
6. | [11 empty] | 6.

## (4) General supplier status
Supplier Overview for Part Number 1: |  | demo part | Supplier Overview for Part Number 2: |  | demo part
Category |  |  | Category
Contracts valid for final production location | Framework Supply Ageement |  | Contracts valid for final production location | Framework Supply Ageement
| Delivery Regulations for order processing |  |  | Delivery Regulations for order processing
| Tool Contract (A/B) |  |  | Tool Contract (A/B)
| Hella Quality Management HP-C-509 |  |  | Hella Quality Management HP-C-509
| Logistics Guideline for OE Suppliers HP-C-516 |  |  | Logistics Guideline for OE Suppliers HP-C-516
Supplier released (for designated Hella Plant) |  |  | Supplier released (for designated Hella Plant)
Approved production location of supplier |  |  | Approved production location of supplier
Requested material / technology released for planned prod.location (e.g. PressFits, PCB, Resin) |  |  | Requested material / technology released for planned prod.location (e.g. PressFits, PCB, Resin)
(last) Audit result / Potential Analysis |  |  | (last) Audit result / potential analysis
Escalation level |  |  | Escalation level
PPM rate (GE global) |  |  | PPM rate (GE global)
Agreed PPM target |  |  | Agreed PPM target
NQE last FY NQE reimbursed last FY |  |  | NQE last FY NQE reimbursed last FY
Experience with product group |  |  | Experience with product group
Supplier Risk Assessment (acc. HF-00432) |  |  | Supplier Risk Assessment (acc. HF-00432)
Logistic Data Sheet (HF-1178_C) |  |  | Logistic Data Sheet (HF-1178_C)
Packaging Data Sheet |  |  | Packaging Data Sheet
Sub-Supplier Management |  |  | Sub-Supplier Management
Product Safety Representative implemented (mandatory projects VW group) |  |  | Product Safety Representative implemented (mandatory projects VW group)
Supplier Overview for Part Number 3: |  | demo part | Supplier Overview for Part Number 4:
Category |  |  | Category
Contracts valid for final production location | Framework Supply Ageement |  | Contracts valid for final production location | Framework Supply Ageement
| Delivery Regulations for order processing |  |  | Delivery Regulations for order processing
| Tool Contract (A/B) |  |  | Tool Contract (A/B)
| Hella Quality Management HP-C-509 |  |  | Hella Quality Management HP-C-509
| Logistics Guideline for OE Suppliers HP-C-516 |  |  | Logistics Guideline for OE Suppliers HP-C-516
Supplier released (for designated Hella Plant) |  |  | Supplier released (for designated Hella Plant)
Approved production location of supplier |  |  | Approved production location of supplier
Requested material / technology released for planned prod.location (e.g. PressFits, PCB, Resin) |  |  | Requested material / technology released for planned prod.location (e.g. PressFits, PCB, Resin)
Risk Management (acc. |  |  | Risk Management (acc.
(last) Audit result / potential analysis |  |  | (last) Audit result / potential analysis
Escalation level |  |  | Escalation level
PPM rate (GE global) |  |  | PPM rate (GE global)
Agreed PPM target |  |  | Agreed PPM target
NQE last FY NQE reimbursed last FY |  |  | NQE last FY NQE reimbursed last FY
Experience with product group |  |  | Experience with product group
Supplier Risk Assessment (acc. HF-00432) |  |  | Supplier Risk Assessment (acc. HF-00432)
Logistic Data Sheet (HF-1178_C) |  |  | Logistic Data Sheet (HF-1178_C)
Packaging Data Sheet |  |  | Packaging Data Sheet
Sub-Supplier Management |  |  | Sub-Supplier Management
Product Safety Representative implemented (mandatory projects VW group) |  |  | Product Safety Representative implemented (mandatory projects VW group)

## (5) Sourcing Approval
Part 1 | demo part | [12 empty] | Part 2 | demo part | [12 empty] | Part 3 | demo part | [12 empty] | Part 4
Project Number |  | demo |  | Project Name | name | Part Number |  |  | demo part |  |  | Part Description | des | Project Number |  | demo |  | Project Name | name | Part Number |  |  | demo part |  |  | Part Description | des | Project Number |  | demo |  | Project Name | name | Part Number |  |  | demo part |  |  | Part Description | des | Project Number | demo |  | Project Name | name | Part Number |  |  |  |  | Part Description
Planned lifetime qty |  |  |  | Cost Share (reg. BOM) |  | Target price (Year 1 per 100) | [5 empty] | Target PVO | 10000 | Planned lifetime qty |  |  |  | Cost Share (reg. BOM) |  | Target price (Year 1 per 100) | [5 empty] | Target PVO |  | Planned lifetime qty |  |  |  | Cost Share (reg. BOM) |  | Target price (Year 1 per 100) | [5 empty] | Target PVO |  | Planned lifetime qty |  |  | Cost Share (reg. BOM) |  | Target price (Year 1 per 100) |  |  |  |  | Target PVO
Nomination Roadmap ID |  |  |  | Concept presented |  | Sourcing Date | [5 empty] | Status drawing |  | Nomination Roadmap ID |  |  |  | Concept presented |  | Sourcing Date | [5 empty] | Status drawing |  | Nomination Roadmap ID |  |  |  | Concept presented |  | Sourcing Date | [5 empty] | Status drawing |  | Nomination Roadmap ID |  |  | Concept presented |  | Sourcing Date |  |  |  |  | Status drawing
# of Suppliers ( in RFQ) |  |  |  | Customer nomination available (PM confirmation) |  | Budget available (PM confirmation) | [5 empty] | Sourcing Level |  | # of Suppliers ( in RFQ) |  |  |  | Customer nomination available (PM confirmation) |  | Budget available (PM confirmation) | [5 empty] | Sourcing Level |  | # of Suppliers ( in RFQ) |  |  |  | Customer nomination available (PM confirmation) |  | Budget available (PM confirmation) | [5 empty] | Sourcing Level |  | # of Suppliers ( in RFQ) |  |  | Customer nomination available (PM confirmation) |  | Budget available (PM confirmation) |  |  |  |  | Sourcing Level
# final offers received | [13 empty] | # final offers received | [13 empty] | # final offers received | [13 empty] | # final offers received
|  |  | Team Proposal |  | Alternative 1 |  | Alternative 2 |  |  |  | Remarks | [5 empty] | Team Proposal |  | Alternative 1 |  | Alternative 2 |  |  |  | Remarks | [5 empty] | Team Proposal |  | Alternative 1 |  | Alternative 2 |  |  |  | Remarks |  |  |  |  | Team Proposal |  | Alternative 1 |  | Alternative 2 |  |  | Remarks
Supplier Name |  |  | ace |  | rosti |  | ata | [6 empty] | Supplier Name | [13 empty] | Supplier Name | [13 empty] | Supplier Name
Currency of quote | [13 empty] | Currency of quote | [13 empty] | Currency of quote | [13 empty] | Currency of quote
Exchange Rate | [13 empty] | Exchange Rate | [13 empty] | Exchange Rate | [13 empty] | Exchange Rate
Final part price / 100pcs | [13 empty] | Final part price / 100pcs | [13 empty] | Final part price / 100pcs | [13 empty] | Final part price / 100pcs
Year 1 | [13 empty] | Year 1 | [13 empty] | Year 1 | [13 empty] | Year 1
Year 2 | [13 empty] | Year 2 | [13 empty] | Year 2 | [13 empty] | Year 2
Year 3 | [13 empty] | Year 3 | [13 empty] | Year 3 | [13 empty] | Year 3
Year 4 | [13 empty] | Year 4 | [13 empty] | Year 4 | [13 empty] | Year 4
Year 5 | [13 empty] | Year 5 | [13 empty] | Year 5 | [13 empty] | Year 5
Tooling & Invest | [13 empty] | Tooling & Invest | [13 empty] | Tooling & Invest | [13 empty] | Tooling & Invest
Pricing first tool set | [13 empty] | Pricing first tool set | [13 empty] | Pricing first tool set | [13 empty] | Pricing first tool set
Number of cavities | [13 empty] | Number of cavities | [13 empty] | Number of cavities | [13 empty] | Number of cavities
Tool ownership | [13 empty] | Tool ownership | [13 empty] | Tool ownership | [13 empty] | Tool ownership
Total pricing add. Invest | [13 empty] | Total pricing add. Invest | [13 empty] | Total pricing add. Invest | [13 empty] | Total pricing add. Invest
Pricing follow up tools | [13 empty] | Pricing follow up tools | [13 empty] | Pricing follow up tools | [13 empty] | Pricing follow up tools
est. # follow up tools | [13 empty] | est. # follow up tools | [13 empty] | est. # follow up tools | [13 empty] | est. # follow up tools
PVO | [13 empty] | PVO | [13 empty] | PVO | [13 empty] | PVO
Total PVO (based on quote) |  |  | 12000 |  | 8000 |  | 10000 | [6 empty] | Total PVO (based on quote) | [13 empty] | Total PVO (based on quote) | [13 empty] | Total PVO (based on quote)
PVO target deviation |  |  | -2000 |  | 2000 |  | 0 | [6 empty] | PVO target deviation | [13 empty] | PVO target deviation | [13 empty] | PVO target deviation
Additional | [13 empty] | Additional | [13 empty] | Additional | [13 empty] | Additional
Cost Break Down | [13 empty] | Cost Break Down | [13 empty] | Cost Break Down | [13 empty] | Cost Break Down
Quick Savings | [13 empty] | Quick Savings | [13 empty] | Quick Savings | [13 empty] | Quick Savings
Negotiated LTA | [13 empty] | Negotiated LTA | [13 empty] | Negotiated LTA | [13 empty] | Negotiated LTA
DPO | [13 empty] | DPO | [13 empty] | DPO | [13 empty] | DPO
APQP Level | [13 empty] | APQP Level | [13 empty] | APQP Level | [13 empty] | APQP Level
Feasibility Study | [13 empty] | Feasibility Study | [13 empty] | Feasibility Study | [13 empty] | Feasibility Study
Main Risks | [13 empty] | Main Risks | [13 empty] | Main Risks | [13 empty] | Main Risks
Final Team Decision | [7 empty] | Share: |  | % |  |  |  | Final Team Decision | [7 empty] | Share: |  | % |  |  |  | Final Team Decision | [7 empty] | Share: |  | % |  |  |  | Final Team Decision | [6 empty] | Share: | %
[8 empty] | Share: |  | % | [11 empty] | Share: |  | % | [11 empty] | Share: |  | % | [10 empty] | Share: | %

## (6) Capacity Management
Part 1 |  | demo part | [5 empty] | Part 2 |  | demo part
|  |  | Customer | Supplier |  | Supplier | HELLA |  |  |  | Customer | Supplier |  | Supplier | HELLA
| Ø Flexibility in % |  | #DIV/0! | #DIV/0! | Shifts per week |  |  |  | Ø Flexibility in % |  | #DIV/0! | #DIV/0! | Shifts per week
| Flexibility leadtime (weeks) |  |  |  | Weeks per year |  |  |  | Flexibility leadtime (weeks) |  |  |  | Weeks per year
| Flexibility duration (weeks) | [7 empty] | Flexibility duration (weeks)
Part 3 |  | demo part | [5 empty] | Part 4
|  |  | Customer | Supplier |  | Supplier | HELLA |  |  |  | Customer | Supplier |  | Supplier | HELLA
| Ø Flexibility in % |  | #DIV/0! | #DIV/0! | Shifts per week |  |  |  | Ø Flexibility in % |  | #DIV/0! | #DIV/0! | Shifts per week
| Flexibility leadtime (weeks) |  |  |  | Weeks per year |  |  |  | Flexibility leadtime (weeks) |  |  |  | Weeks per year
| Flexibility duration (weeks) | [7 empty] | Flexibility duration (weeks)

## (7) Counter measures
No | Part No | Description | Target | Value over target | Currency | Activities | Value of counter measure | Currency | Final due date | Degree of fulfillment | Responsible
1
2
3
4
5
6
7
8
9
10

## (8) Team Recommendation
Department | Name | Recommended Supplier
Program Purchasing
Project Management
Material Group Specialist / Management
Product Cost Management
SQA TtM
Mechanical Design (if applicable)
Hardware Design (if applicable)
Plant Logistics
Manufacturing Engineer
Final Decision: Project Team

## (9) Open points and activities
Topic | Responsible | Due Date

## Doc info
No of document | Process assignment | Edition date | Designer of HF | PLD of related process | PDE of related Process
HF-00026_GE | I2P-20-40-10 | 2017-11-24 | Sonia Vargas Galvez | Sonja Vargas Galvez, Klaus Mensing, Maik Froese | Lars-Arne Willer, Klaus Mensing, Thorsten Suewolto
HF-00026_GE | I2P-20-40-10 | 2018-12-12 | Sonia Vargas Galvez | Sonja Vargas Galvez, Klaus Mensing, Maik Froese | Lars-Arne Willer, Klaus Mensing, Thorsten Suewolto

## Sourcing_Meeting_Minutes
Sourcing Board GE – Meeting Minutes |  |  |  | 2019-11-26
Strategy | [6 empty] | Current Sourcing Level |  |  | Project Team
Sourcing | [6 empty] | Highest Sourcing Level |  |  | Project Team
Project Number |  |  |  |  | demo
Project Name |  |  |  |  | name
Segment / Product Group
Part Number |  |  |  |  | demo part
Part Description |  |  |  |  | des
ID Nomination Roadmap |  |  |  |  | 0
In case of combined / bundled projects or parts enter the data separated by „ ; “
Participants:
Name |  | Function |  | Type (P / T) |  | Name |  | Function |  | Type (P / T)
0 |  | PJM |  |  |  | 0 |  | PUR
0 |  | MD | [5 empty] | MGS
0 |  | SQA | [5 empty] | MGS-SQA
0 |  | PCM | [5 empty] | MGM
0 |  | ME
0 |  | LOG
Protocol Sourcing Meeting:
No | Topic |  | Description | [7 empty] | Type(I/D)
1 | Project Highlight |  | qty issue xxx. cost issue xxx. | [7 empty] | I
2 | Project Timing |  | timing issue | [7 empty] | I
3 | Supplier Selection |  | ace/rosti/ata | [7 empty] | I
4 | Commercial Result |  | Target PVO |  | ace |  | rosti |  | ata |  | I
|  |  | 10000 |  | 12000 |  | 8000 |  | 10000
|  |  | Saving => |  | -2000 (-20%) |  | 2000 (20%) |  | 0 (0%)
5 | Team Decision |  | The team propose to go demo part for ace. | [7 empty] | D
Further actions and tasks:
No | Topic |  | Description |  |  |  |  | Responsible |  | Due Date
1 | Purchasing |  | Finalize nomination letter with supplier. |  |  |  |  | 0
2
3