## Risk Evaluation
Risk Evaluation Components |  |  | Project: | LE_LED/HKG N60AB LED ECU(MDLC_HSE)
Pos. |  |  |  |  | 1
Part Number (xxx.xxx-xx) + Drawing-Index |  |  |  |  | 209.587-10 |  | 240.987-00 |  | 240.988-00 |  | 240.989-00 |  | 240.990-00
Part Description |  |  |  |  | DICHTRING 67,2X37,5 |  | ABDECKUNG (BJEV-ECU) |  | KUEHLKOERPER (BJEV-ECU) |  | ABDECKUNG TUNERBOX (BJEV-ECU) |  | EZ-LEITERPLATTE (BJEV-ECU)
Commodity Group |  |  |  |  | RUB_STA |  | TECH_PLAS |  | DIE_CASTING |  | STAMP_PART |  | PCB
Average quantity / a |  |  |  |  | 115189 |  | 115189 |  | 115189 |  | 115189 |  | 115189
Target cost [€/100 pcs.] |  |  |  |  | 11.9165 |  | 47.9115 |  | 152.3342 |  | 30.0983 |  | 128.9926
Project life time [years] |  |  |  |  | 5 |  | 5 |  | 5 |  | 5 |  | 5
Production plant Hella |  |  |  |  | 1111 |  | 1111 |  | 1111 |  | 1111 |  | 1111
C- samples [mm.yyyy] |  |  |  |  | 08.2019 |  | 12.2019 |  | 11.2019 |  | 09.2019 |  | 10.2019
SOP Hella [mm.yyyy] |  |  |  |  | 09.2020 |  | 09.2020 |  | 09.2020 |  | 09.2020 |  | 09.2020
Raw material (acc. to current drawing version) |  |  |  |  | Undefined |  | Undefined |  | Undefined |  | Undefined |  | Undefined
MGM (Purchasing) |  |  |  |  | PlzUpdate |  | PlzUpdate |  | PlzUpdate |  | PlzUpdate |  | PlzUpdate
Series Purchasing (MGS) |  |  |  |  | PlzUpdate |  | Jerry Fang |  | PlzUpdate |  | PlzUpdate |  | Sylvia Xi
Project Purchasing |  |  |  |  | ZHANSH70 |  | ZHANSH70 |  | ZHANSH70 |  | ZHANSH70 |  | ZHANSH70
General comment
[5 empty] | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps: |  | Manufacturing steps:
I | Risk Assessment | Please rate the criticality according to the following general scale: (additional explanation given within the single steps) 0 - not critical / irrelevant for the scope / low requirements; 1 - critical / medium requirements; 2- very critical/ high requirements |  |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in |  | >> Please type in
| Main criteria |  | Evaluation point | Description | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments | Ranking | Comments
1 | Technology and design related criteria | 1.1 | Risk: Complexity | Amount and character of functions, level of system integration 0 pts: "simple" part without any further technical function to the product 1 pt: further technical function to the product is given 2 pts: further technical function incl. safety aspects given | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 1.2 | Risk: Technology | Implemented technology, raw material and resulting relevance of function is … 0 pts: ... already known to Hella and existent suppliers 1 pt: ... new to Hella; current supplier portfolio is experienced 2 pts: ... new to Hella; current supplier portfolio not experienced | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 1.3 | Expected design changes (internal maturity level) | High number of changes expected because of a high influence on/of other supply levels (e.g. standard electronical parts), dependant systems, geometry determining parts, density- and noise relevance? 0 pts: no, the design is already fixed 1 pt: few design changes are expected but won't have a major influence on upcoming sourcing activities 2 pts: several design changes are expected during sourcing phase that most likely might effect strategy and/or supplier choice | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 1.4 | Raw material (mentioned on current drawing version) | Is the requested material generally available or are there possible regional differences? 0 pts: common material which is usually available per requested sourcing region as well as for suppliers 1 pt: material should be available per sourcing region but not common for every supplier 2 pts: material is globally only limited available | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 1.5 | Technical Cleanliness | Is technical cleanliness relevant for the reliability and needs to be considered? 0 pts: no specific technical cleanliness requirements beside regular 5S [Hella cleanliness class 0-1; metallic <= 1.000 µm; non-metallic <= 1.500 µm] AND no additional effort expected 1 pt: medium high technical cleanliness requirements beside regular 5S [Hella cleanliness class 2; metallic <= 600 µm; non-metallic <= 1.000 µm] OR cleanliness requirements can be kept by used technologies and cleaning processes; smaller optimizations needed, medium effort expected 2 pts: high technical cleanliness requirements beside regular 5S [Hella cleanliness class 3; metallic <= 400 µm; non-metallic <= 600 µm] OR major gap between cleanliness requirements and existing capability of used technologies & processes, high effort expected | 0
2 | Supplier related criteria | 2.1 | New supplier a) general usage of new supplier b) due to new technology (choose option a or b) | a) general usage of new supplier 0 pts: new supplier could be chosen for part 1 pt: new supplier could be chosen; needs additional attention 2 pts: new supplier should not be taken into account for this part | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  |  |  | b) new supplier requested due to new technology (see 1.2) 0 pts: new supplier could be chosen for part 1 pt: new supplier could be chosen; needs additional attention 2 pts: new supplier should not be taken into account for this part | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 2.2 | Development support / capacity of supplier | Development support by supplier needed? 0 pts: further support from supplier in basic part development not needed; only regular supplier know-how such as tool concept etc. needed 1 pt: support regarding part development from supplier needed partially; independent of tooling concepts etc. 2 pts: support regarding (concept) development from supplier expected to be high | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 2.3 | Sub-Supplier Management (according to mentioned manufacturing steps) | 0 pts: part requires no further supply chain 1 pt: part contains manufacturing steps that possibly lead to further supply chain (which most likely needs to be tracked) 2 pts: part requires further supply chain that needs to be tracked due to needed technology è Please add comment regarding corresponding manufacturing step | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
3 | Supplier production related criteria | 3.1 | Production Testing | Are special testings or processes needed/requested at supplier side in addition to normal production controls? (e.g. tumble circle, tight position tolerance, camera checks...) 0 pts: no, no further testing/inspection requried 1 pt: single production steps should be inspected additionally 2 pts: the whole production process needs to be completely checked afterwards è Please add comment about the requested inspection | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 3.2 | Level of automation | 0 pts: no specific requirements / manual handling during production is possible 1 pt: medium level of automation necessary / manual handling during production not recommended 2 pts: high level of automation needed / manual handling during production not allowed | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 3.3 | Packaging Concept | Do we require a specific packaging concept in order to fulfill e.g. cleanliness requirements or specific handling at Hella production line? 0 pts: no specifics required // normal bulk packaging sufficient 1 pt: part specific (ESD) trays needed // no further requirements 2 pts: part specific trays needed as well as maintaining of concrete cleanliness specifications | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 3.4 | Infrastructure / transportation | 0 pts: no specific requirements due to infrastructure 1 pt: special requirements possible and tbd 2 pts: local supplier mandatory | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
4 | Date related criteria | 4.1 | Project timing | Does the general project timing schedule put the lead time of the single part in danger? 0 pts: no, the timing for development and build up of the single part is matching within project timing schedule 1 pt: the timing for development and build up of the single part can only be managed by already using buffered timing within project schedule but milestones are likely to be kept 2 pts: the timing for development and build up of the single part is NOT matching with project timing schedule and will most likely put it in danger | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 4.2 | Procurement time manufacturing facility/appliances | Do specific lead times for equipment etc. which are required at the supplier have to be considered? 0 pts: no additional specific equipment apart from needed toolings are required 1 pt: further equipment apart from needed toolings is required but the timeline is still sufficient to keep the overall project timing schedule 2 pts: further equipment apart from needed toolings is required and will most likely put the overall projet timing schedule in danger | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 4.3 | Lessons Learned in comparable projects | Did similar projects / parts show risks in timing in the past? 0 pts: previous projects with similar parts did not show any problems or road blockers 1 pt: previous projects with similar parts did have slight problems but could be solved within project timing without bigger consequences 2 pts: previous projects with similar parts did have problems which caused ongoing consequences to the program | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
5 | Variabel criteria (to be chosen individually) | 5.1 | Please describe topic | Please insert description and rank according to team recommendation with 0 - 2 pts | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
|  | 5.2 | Please describe topic | Please insert description and rank according to team recommendation with 0 - 2 pts | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Classification
| Low | 0 | 7 | Evaluation Score
| Medium | 8 | 15 | Criticality
| High | 16 |  | Comment
II | Project Sourcing Strategy
| Sourcing strategy |  | Lever |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy |  | Ranking sourcing strategy
1 | Summary MGS-strategy for (sub-)commodity | 1.1 | Main lever |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS
|  | 1.2 | Second lever |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS
|  | 1.3 | Third lever |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS
|  | 1.4 | Additional comments to MGS-strategy // involvement MGS regarding raw material |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS |  | >> To be entered by input from responsible MGS
2 | Determination of project sourcing strategy | Please rank each strategy criteria in the second column from 1 (= 1st rank) to 7 (= 7th rank)
|  | 2.1 | Number of suppliers |  | >>Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank
|  | 2.2 | Sourcing Area |  | >>Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank
|  | 2.3 | Maturity of product at nomination time (e.g. do we require a high maturity of the part or do we rather focus on early sourcing?) |  | >>Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank
|  | 2.4 | Involvement of Development Supplier (use of Concept Competition) |  | >> Please select | >> Please rank | >> Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank
|  | 2.5 | Bundling options |  | >>Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank | >> Please select | >> Please rank
|  | 2.6 | Last Call (i.e. any supplier within the group who would get a last call?) |  | >> Please select | >> Please rank | >> Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank | >>Please select | >> Please rank
|  | 2.7 | Others |  | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank | >> Please type in | >> Please rank
III | Overview for Sourcing Board Reporting
1 | Summary Criticality | 3.1 | Criticality
2 | Summary Nomination Strategy | 2.1 | Top 1 Strategy
|  | 2.2 | Top 2 Strategy
|  | 2.3 | Top 3 Strategy
3 | Sourcing Board level | 3.1 | Sourcing Board level